## Project Backlog
OMCS Product Backlog
No. | Category | Userstory | Description | Acceptance criteria | Delivery date | Sprint
1 | Document | Report 1 | As a team member, I want to have the introduction about the project so that I can understand the initial idea. | The report should follow the template from FPT University Good layout, cover all items | 20 May, 2014 | 1
2 |  | Report 2 | As a team member, I want to have the Project Management Plan so that I can work well on the project | The report should follow the template from FPT University Good layout, cover all items | 05 June, 2014 | 2, 3
3 |  | Report 3 | As a team member, I want to have the System Requirements Specifications | The report should follow the template from FPT University Good layout, cover all items All features are listed out and analysed carefully | 12 June, 2014 | 3, 4
4 |  | Report 4 | As a team member, I want to have the System Design Specifications so that I can have a good design to follow | The report should follow the template from FPT University Good layout, cover all items | 09 July, 2014 | 4, 5, 6, 7, 8
5 |  | Report 5 | As a team member, I want to have System Implementation & Test document so that I can have full-featured and well-tested release | The report should follow the template from FPT University Good layout, cover all items | 09 July, 2014 | 9, 10
6 |  | Report 6 |  |  | 05 June, 2014 | 2, 3
|  | Team document | As a team member, I want to have some document (product backlog, sprint backlog, team wiki) created. So I can work well on OMCS |  |  | 1
7 | Feature | [User] Login | As a user, I want to login to the system |  |  | 1
8 |  | [User] Login with remember me | As a user, I want to login automatically
9 |  | [User] Register | As a guest, I want to register new account |  |  | 1
10 |  | [User] Forget password | As a user, I want to get new password by email when I forgot it, so that I can continue to use OMCS |  |  | 1
|  | [User] Edit profile information | As a user, I want to update some information (profile picture, firstname,…) |  |  | 1
11 |  | [Patient] Update patient information | As a patient, I want to update some information about my profile, basic health record | For user experience, use in-place editor to edit information
12 |  | [Patient] Chat | As the user, I want to chat with doctor realtime So I can send message and doctor receive immediately | The behavior could be: The system list out all doctors with their status Patient can select doctor to chat with Patient can see old chat content
13 |  | [Patient] Share webcam | As a patient, I want to share my webcam so the information's exchange is more easier | Doctor can see the stream that patient share Doctor can see the stream in full-screen
15 |  | [Patient] Attachment | As a patient, I want to attach some files, images and send to doctor | If attach files are images, display on the chat content, otherwise, let doctor download it
[Admin] Define medical profile template
|  | Create medical profile | As the doctor, I want to create medical profile for patient
|  | Manage doctor | As the admin, I want to add, manage doctors
| Design | Basic design | As the PO, I want to see the basic design of system

## Impediment Backlog
Group 2 Impediment
No. | Status | Description
1 | Not solve | Some daily meeting late more than 20 minutes
2 | Not solve | Not follow convention when commit code to SVN
3 | Not solve | When finish task, not commit to SVN for other member verify it
Daily Meeting |  | Absent Without Plans | Absent With Plans
13/05 |  | Tín
14/5 |  | Tin
15/5
16/5
17/5 |  | Dang
18/5
19/05 |  |  | Tin
20/05 |  | Tin
21/05 |  | Tin
22/5
23/5
24/5
25/5 |  |  | Tin
26/5 |  |  | Dang
27/05 |  | Tin
28/05
29/05