## Impediment Backlog
Group 2 Impediment
No. | Status | Description | Created Date
1 | Solve | Some daily meeting late more than 20 minutes | 16 May, 2014
2 | Solve | Not follow convention when commit code to SVN | 15 May, 2014
3 | Not solve | When finish task, not commit to SVN for other member verify it | 10 June, 2014
4 | Solve | Stuck in define medical profile template | 15 June, 2014
5 | Not solve | Trello cannot create subtask | 25 June, 2014
6 | Not solve | Losing member | 20 July, 2014
7 | Solve | Cannot reuse some previous report | 05 August, 2014
Daily Meeting |  | Absent Without Plans | Absent With Plans
13/05 |  | Tín
14/5 |  | Tin
15/5
16/5
17/5 |  | Dang
18/5
19/05 |  |  | Tin
20/05 |  | Tin
21/05 |  | Tin
22/5
23/5
24/5
25/5 |  |  | Tin
26/5 |  |  | Dang
27/05 |  | Tin
28/05
29/05