## Project Backlog
OMCS Product Backlog
No. | Category | Userstory | Description | Acceptance criteria | Delivery date | Sprint
1 | Document | Report 1 | As a team member, I want to have the introduction about the project so that I can understand the initial idea. | The report should follow the template from FPT University Good layout, cover all items | 20 May, 2014 | 1
2 |  | Report 2 | As a team member, I want to have the Project Management Plan so that I can work well on the project | The report should follow the template from FPT University Good layout, cover all items | 05 June, 2014 | 2, 3
3 |  | Report 3 | As a team member, I want to have the System Requirements Specifications | The report should follow the template from FPT University Good layout, cover all items All features are listed out and analysed carefully | 12 June, 2014 | 3, 4
4 |  | Report 4 | As a team member, I want to have the System Design Specifications so that I can have a good design to follow | The report should follow the template from FPT University Good layout, cover all items | 09 July, 2014 | 4, 5, 6, 7, 8
5 |  | Report 5 | As a team member, I want to have System Implementation & Test document so that I can have full-featured and well-tested release | The report should follow the template from FPT University Good layout, cover all items | 09 July, 2014 | 9, 10
6 |  | Report 6 |  |  | 05 June, 2014 | 2, 3
7 |  | Team document | As a team member, I want to have some document (product backlog, sprint backlog, team wiki) created. So I can work well on OMCS | Product backlog with detail description, acceptance criteria, and delivery date Sprint backlog with breaked tasks with assignee |  | 1
8 | Feature | [User] Login | As a user, I want to login to the system | Login using email After login, redirect user based on their role |  | 1
9 |  | [User] Login with remember me | As a user, I want to login automatically
10 |  | [User] Logout | As a user, I want to logout
11 |  | [User] Register | As a guest, I want to register new account | Only required some basic information Send email to confirm email address Use capcha to enhanced security |  | 1
12 |  | [User] Forget password | As a user, I want to get new password by email when I forgot it, so that I can continue to use OMCS | Send email with gerenated new password |  | 1
13 |  | [User] Edit profile information | As a user, I want to update some information (firstname, address…) | Validate required fields, number |  | 1
14 |  | [Patient] View medical profile | As a patient, I want to view my medical profile, so that I can have overview about my dieases | List all medical profiles created for logged in patient Not allow patient to modify medical profile
15 |  | [Patient] View linked medical profile information | As a patient, I want to extract some information (immunization, allegy) so that I can quickly have overview about them | Only show medical profile that use built-in modules (immunization, allergy) Link to medical profile that have extracted information
16 |  | [Patient] Update patient information | As a patient, I want to update some information about my profile, basic health record | For user experience, use in-place editor to edit information
17 |  | [Patient] Chat | As the user, I want to chat with doctor realtime So I can send message and doctor receive immediately | The behavior could be: The system list out all doctors with their status Patient can select doctor to chat with Patient can see old chat content
18 |  | [Patient] Show webcam | As a patient, I want to share my webcam so the information's exchange is more easier | Doctor can see the stream that patient share Doctor can see the stream in full-screen
19 |  | [Patient] Upload attachment | As a patient, I want to attach some files, images and send to doctor | If attach files are images, display on the chat content, otherwise, let doctor download it
20 |  | [Patient] View consult history | As a patient, I want to see previous chat content with doctor, so that I haven't to remember everything | List all chat content with the sent time Sort chat message by time
21 |  | [Patient] View doctor online | As a patient, I want to see who is online, so that I can get quickly response | When doctor go to Conversation page, their status is shown as online for patient Patient can see status real-time, donot need to refresh the page
22 |  | [Patient] Change profile picture | As a patient, I want to change my profile picture
23 |  | [Patient] Change password | As a patient, I want to change my password | Patient have to re-enter current password Patient have to enter new password twice
24 |  | [Patient] Rating doctor | As a patient, I want to rate doctor for his consulting | Maximum point is 5 Doctor and other patients can see the average point of rating
25 |  | [Patient] Comment doctor | As a patient, I want to give my comment for doctor so that I can show my opinions/ideas | Doctor and other patients can see the comment Doctor can comment to reply
26 |  | [Doctor] Chat | As a doctor, I want to chat with patients so that I can help them | Doctor can see unread messages
27 |  | [Doctor] Request webcam | As a doctor, I want to request camera from patients when needed | Only request to one patient at the same time
28 |  | [Doctor] Upload attachment | As a doctor, I want to upload attachment and send to patient, so useful data could be exchange | If attach files are images, display on the chat content, otherwise, let patient download it
29 |  | [Doctor] Create medical profile | As a doctor, I want to create medical profile for patient, so that I can update it instantly | Doctor can choose any exsting template to create One patient with have only one medical profile created from one template
30 |  | [Doctor] View medical profile | As a doctor, I want to view medical profile of a patient, so that I can have overview about his diseases | Doctor can view medical profile created by other doctors
31 |  | [Doctor] Update medical profile | As a doctor, I want to update medical profile created for patient
32 |  | [Doctor] Create patient | As a doctor, I want to create account for patient so that new patient can use application instanly | Password of patient is sent to patient's email automatically
33 |  | [Doctor] Edit patient information | As a doctor, I want to edit patient information, so that I can correct information
34 |  | [Doctor] View comment/rating | As a doctor, I want to view comment/rating so that I can know feedback from patients
35 |  | [Doctor] Add comment | As a doctor, I want to add new comment so that I can interact with my patients effectively
36 |  | [Doctor] Search patient | As a doctor, I want to search patient so that I can increase my work performance
37 |  | [Doctor] Change picture profile | As a doctor, I want to change my profile picture
38 |  | [Doctor] Change password | As a doctor, I want to change my password | Doctor have to re-enter current password Doctor have to enter new password twice
39 |  | [Admin] View medical profile | As an admin, I want to view medical profile from all patients for management
40 |  | [Admin] Create doctor | As an admin, I want to create new doctor for my hospital | Admin can edit some information during add new doctor
41 |  | [Admin] Edit doctor | As an admin, I want to edit information of a doctor, so that I can correct wrong information
42 |  | [Admin] Search doctor | As an admin, I want to search doctors so that I can increase my work performance
43 |  | [Admin] Deactive/Active doctor | As an admin, I want to deactive/active doctor, so that I can operate system well | Deactive doctor cannot access to the system anymore
44 |  | [Admin] Create patient | As an admin, I want to create new patient
45 |  | [Admin] Edit patient | As an admin, I want to edit some information of patient
46 |  | [Admin] Search patient | As a admin, I want to search patient so that I can increase my work performance
47 |  | [Admin] Deactive/Active patient | As an admin, I want to deactive/active patient, so that I can operate system well | Deactive patient cannot access to the system anymore
48 |  | [Admin] Define medical profile template | As an admin, I want to define new medical profile template for my hospital | Template can re-use existing information from patients Template can use some built-in modules of system
49 |  | [Admin] Update medical profile template | As an admin, I want to update medical profile template, so that my template can stay update with new changes | After updating, a summary changes should be listed out
50 |  | [Admin] Change picture profile | As an admin, I want to change my profile picture
51 |  | [Admin] Change password | As an admin, I want to change my password | Admin have to re-enter current password Admin have to enter new password twice