## Sprint 1
Sprint 1 Kanban: https://trello.com/b/JditEulN/kanban-sprint-1 | [6 empty] | Start date: 14 May End date: 20 May Commit: 20 points Estimate: 25 points Deliver: ? points
No. | Userstory | Task | Description | Acceptance criteria | Assign | Estimate | Status
1 | Report 1 | Finish report 1 | Update report with new changes: - Change scope from public to a support for one hospital - Doctor will create medical profile for patient |  | Su | 2 | Accept
2 |  | Verify report |  |  | Danh | 1 | Accept
3 | Team document | Create product backlog, Sprint 1 backlog |  |  | Su | 1 | Accept
4 | Project skeleton | Create project structure and commit to SVN |  | Every member can checkout and run successfully | Su | 3 | Accept
5 | Chat realtime | Research and work around with SignalR | Follow this instruction: http://tech.pro/tutorial/1491/chat-application-with-signalr-and-aspnet-mvc-4 Try to understand technology, how to apply it? |  | Danh | 3 | Done
6 | Chat with video stream | Research and work around with WebRTC | Follow this instruction: http://www.skylinetechnologies.com/Blog/Article/48/Peer-to-Peer-Media-Streaming-with-WebRTC-and-SignalR.aspx Try to understand technology, how to apply it? |  | Dang | 3 | Done
7 | Create medical profile | Define the structure of a medical profile | Get some common information from some hospitals and analyse them |  | Tin | 4 | Done
8 | Report 2 | Research about "skin infections, rashes diseases" | Try to some these information (all metric is in Vietnam): Find some popular skin infections, rashes diseases (based on reliable resource). Ratio skin infections, rashes diseases / normal diseases What is "treatment regimen" (phác đồ điều trị) for each popular diseases. |  | Danh | 2 | Done
9 | Report 2 | Research about "chronic diseases" | Try to some these information (all metric is in Vietnam): Find some popular chronic diseases (based on reliable resource). Ratio chronic diseases / normal diseases What is "treatment regimen" (phác đồ điều trị) for each popular diseases. |  | Tin | 2 | Todo
10 | Report 2 | Research about other diseases/medical treatment | Try to get these information (all metric is in Vietnam): What are other diseases that need to go to hospital quite often? Can those easily conduct via internet? |  | Dang | 2 | Todo
11 | Login | Login as User/Admin/Doctor | As the user, I want to login to the system |  | Su | 2 | Done
25

## Sprint 2
Sprint 2 Kanban: https://trello.com/b/JditEulN/kanban-sprint-1 | [6 empty] | Start date: 20 May End date: 27 May
No. | Userstory | Task | Description | Acceptance criteria | Assign | Estimate | Status
1 |  | Usecase Overview |  |  | Su | 2 | Done
2 |  | Create Entity Relation Diagram | As the developer, I want to have a database schema of OMCS |  | Danh | 2 | Done
3 |  | Mockups UI | HTML + CSS |  | Tin |  | Accept
4 |  | Draft physical database |  |  | Su |  | Done
5 |  | Research "Add/Remove element on HTML page" |  |  | Dang
6
7
8
9
10
11
12
4

## Sprint 3
Sprint 3 Kanban: https://trello.com/b/JditEulN/kanban-sprint-1 | [6 empty] | Start date: 27 May End date: 05 Jun
No. | Userstory | Task | Description | Acceptance criteria | Assign | Estimate | Status
1 |  | Fix ERD Diagram |  |  | Danh | 2 | Accept
2 |  | Fix Physical Database Diagram |  |  | Su | 2 | Accept
3 |  | Update Usecase Diagram |  |  | Su |  | Accept
4 |  | Use case for Patient |  |  | Dang |  | Accept
5 |  | Usecase for Doctor |  |  | Danh |  | Accept
6 |  | Usecase for Admin/Authorized User/Guest |  |  | Tin |  | Accept
| Implement basic function for mockups | Register |  |  | Su |  | Accept
7 |  | Manage Doctor |  |  | Dang
8 |  | Finish report 2 |  |  | Dang |  | Accept
9 |  | Finish custom form for medical profile |  |  | Su |  | Accept
10 |  | Class diagram |  |  | Danh |  | Accept
11 |  | Merge Use case (report 3)
12
4

## Sprint 4
Sprint 4 Kanban: https://trello.com/b/JditEulN/kanban-sprint-1 | [6 empty] | Start date: 05 Jun End date: 12 Jun
No. | Userstory | Task | Description | Acceptance criteria | Assign | Estimate | Status
1 |  | System architecture |  |  | Su | 2 | Done
2 |  | Component Diagram |  |  | Su | 2 | Accept
3 |  | Class diagram Model |  |  | Danh |  | Accept
4 |  | Sequence diagram | Define new medical profile template Update medical profile for patient View medical profile Request an online medical treatment Update Personal Health Record |  |  |  | Accept
5 |  | Manage user | Create, Edit, Deactive User, Assign Role for User |  | Dang |  | Accept
6 |  | Manage doctor | Add, Edit, Deactive Doctor |  | Tin
7 |  | Manage SpecialtyField | Add Specialty, Assign SpecialtyField for Doctor |  | Su |  | Accept
8 |  | Create patient style |  |  | Su |  | Accept
9 |  | Finish report 3
10
11
12
4

## Sprint 5
Sprint 5 Kanban: https://trello.com/b/JditEulN/kanban-sprint-1 | [6 empty] | Start date: 12 Jun End date: 19 Jun
No. | Userstory | Task | Description | Acceptance criteria | Assign | Estimate | Status
1 |  | Patient update Personal Health Record |  |  | Su | 2 | Accept
2 |  | Layout Homepage |  |  | Dang | 2 | Accept
3 |  | Chatting |  |  | Danh |  | Done
4 |  | New medical profile template |  |  | Su |  | Accept
5 |  | Update system architecture |  |  | Su |  | Accept
6 |  | Manage doctor | Add, Edit, Deactive Doctor |  | Tin |  | Done
7 |  | Class diagram Business Logic, Controller |  |  | Danh |  | Done
8 |  | Show Conversation List for Patient |  |  | Dang |  | Done
9 |  | Manage FilmType |  |  | Dang |  | Accept
10
11
12
4

## Sprint 6
Sprint 6 Kanban: https://trello.com/b/JditEulN/kanban-sprint-1 | [6 empty] | Start date: 19 Jun End date: 03 Jul
No. | Userstory | Task | Description | Acceptance criteria | Assign | Estimate | Status
1 |  | Finish Chatting |  |  | Danh | 2 | Accept
2 |  | Doctor create medical profile for patient |  |  | Su | 2 | Accept
3 |  | Let user show webcam on conversation
4 |  | Manage doctor |  |  | Tin |  | Accept
5 |  | Show Conversation List for Patient |  |  | Dang |  | Accept
6 |  | Show Allergy List on UserHealthRecord page |  |  | Danh |  | Accept
7
8
9
10
11
12
4

## Sprint 7
Sprint 7 Kanban: https://trello.com/b/JditEulN/kanban-sprint-1 | [6 empty] | Start date: 03 Jul End date: 09 Jul
No. | Userstory | Task | Description | Acceptance criteria | Assign | Estimate | Status
1 |  | Add modules Immunization to MedicalProfile
2 |  | Add modules FilmDocument to MedicalProfile
3 |  | Add modules Allergy to MedicalProfile
4 |  | Add captcha for register user
5 |  | Show Immunization List on UserHealthRecord page
6 |  | Show list medical profile on patient page
7 |  | Add attachment in chatting
8 |  | Let user show webcam on conversation
9 |  | Update sequence diagram
10
11
12
0

## Sprint 8
Sprint 8 Kanban: https://trello.com/b/lnBdUvYc/sprint-8 | [6 empty] | Start date: 09 Jul End date: 17 Jul
No. | Userstory | Task | Description | Acceptance criteria | Assign | Estimate | Status
1 |  | Show list medical profile in patient page
2 |  | Update sequence diagram
3 |  | Fix layout
4 |  | Update usecase diagram
5 |  | Define some REAL medical profile template to use
6 |  | Finish show webcam | Doctor can see the stream from patient
7 |  | Change layout homepage + login
8 |  | Profile picture chỉ lưu tên ảnh + GetPictureUrl
9 |  | Manage allergy type
10
11
12
0

## Sprint 9
Sprint 9 Kanban: https://trello.com/b/reAEHfJG/sprint-9 | [6 empty] | Start date: 17 Jul End date: 24 Jul
No. | Userstory | Task | Description | Acceptance criteria | Assign | Estimate | Status
1 |  | Patient Vote/Comment
2 |  | Manage Medical Profile for Admin/Doctor
3 |  | Forget password
4 |  | Finish register
5 |  | Update ERD
6 |  | Doctor add/edit new patient with personal health record | Doctor can see the stream from patient
7 |  | Show list medical profile in patient page
8 |  | Report 5
9 |  | Refactor all linked information in personal health record
10
11
12
0

## Sprint 10
Sprint 10 https://trello.com/b/t0qVHCTb/sprint-10 | [6 empty] | Start date: 24 Jul End date: 31 Jul
No. | Userstory | Task | Description | Acceptance criteria | Assign | Estimate | Status
1 |  | Edit hospital information
2 |  | Use email as username to login
3 |  | Add 404 page, Access denied page
4 |  | Patient vote/comment doctor
5 |  | Measure performance using Jmeter
6 |  | Fix bug manage Doctor. Can update Specialty Field for doctor
7 |  | Show list medical profile in patient page
8 |  | Finish report 5
9
10
11
12
0

## Sprint 11
Sprint 11 https://trello.com/b/ixZwjrKr/sprint-11 | [6 empty] | Start date: 31 Jul End date: 0? Jul
No. | Userstory | Task | Description | Acceptance criteria | Assign | Estimate | Status
1 |  | Change layout admin
2 |  | Change layout doctor
3 |  | Update layout (Scrollbar, Message info when ajax)
4 |  | Doctor See Comment and Rating from Patient
5 |  | Admin manage hospital Information
6 |  | Admin Manage Comment
7 |  | Admin/Doctor/Patient can edit profile
8 |  | Ajax upload image
9 |  | Create sprint backlog, product backlog
10 |  | Update meeting minutes
11 |  | Create document about user interface
12 |  | Create task sheet
13 |  | Define report 6 struture
14 |  | Final Report
15 |  | Update sequence diagram
16 |  | Show hospital information on Medical Profile page
0

## Information
Member |  |  | Information
No. | Short Name | Fullname | 1. Kanban | https://trello.com/b/JditEulN/kanban-sprint-1
1 | Su | Trần Nguyên Tiến Sứ | 2. Velocity | 1 point/day
2 | Danh | Trần Cao Danh
3 | Dang | Trương Hải Đăng
4 | Tin | Bùi Nguyên Tín
Status
Todo
In-progress
Verify
Done
Accept