## Project Backlog
OMCS Product Backlog
No. | Category | Userstory | Description | Value | Risk | Sprint
1 | Document | Report 1 |  | 200 |  | 1
2 |  | Report 2 |  | 200 |  | 2
3 |  | Report 3 |  | 200 |  | 2
4 |  | Report 4 |  | 10
5 |  | Report 5 |  | 10
6 |  | Report 6 |  | 10
|  | Team document | As a developer, I want to have some document (product backlog, sprint backlog) created. So I can work well on OMCS | 200 |  | 1
7 | Function | Project skeleton | As a developer, I want run OMCS successful on my computer | 100 |  | 1
8 |  | Login | As the user, I want to login to the system | 100
9 |  | Chat realtime | As the user, I want to chat with doctor realtime So I can send message and doctor receive immediately | 10 | 20 | 1
10 |  | Send image in chat conversation | As the user, I want to attach image and send to doctor. So the doctor can see it immediately. | 10 | 20 | 1
|  | Chat with video stream | As the user, I want to use my webcam to made a video meeting with my doctor. So the information's exchange is more easier |  |  | 1
11 |  | Create medical profile | As the doctor, I want to create medical profile for patient | 10 | 100
12 |  | Manage doctor | As the admin, I want to add, manage doctors | 10 | 20
13 | Design | Basic design | As the PO, I want to see the basic design of system | 100
15

## Impediment Backlog
Group 2 Impediment
No. | Status | Description
1 | Not solve | Some daily meeting late more than 20 minutes
2 | Not solve | Not follow convention when commit code to SVN
3 | Not solve | When finish task, not commit to SVN for other member verify it
Daily Meeting |  | Absent Without Plans | Absent With Plans
13/05 |  | Tín
14/5 |  | Tin
15/5
16/5
17/5 |  | Dang
18/5
19/05 |  |  | Tin
20/05 |  | Tin
21/05 |  | Tin
22/5
23/5
24/5
25/5 |  |  | Tin
26/5 |  |  | Dang
27/05
28/05