## Sprint 1
Sprint 1 Kanban: https://trello.com/b/JditEulN/kanban-sprint-1 | [6 empty] | Start date: 14 May End date: 20 May Commit: 20 points Estimate: 22 points Deliver: ? points
No. | Userstory | Task | Description | Acceptance criteria | Assign | Estimate | Status
1 | Report 1 | Finish report 1 | Update report with new changes: - Change scope from public to a support for one hospital - Doctor will create medical profile for patient |  | Su | 2 | Todo
2 |  | Verify report |  |  |  | 1 | Todo
3 | Team document | Create product backlog, Sprint 1 backlog |  |  | Su | 1 | Done
4 | Project skeleton | Create project structure and commit to SVN |  | Every member can checkout and run successfully |  | 3 | Todo
5 | Chat realtime | Research and work around with SignalR | Follow this instruction: http://tech.pro/tutorial/1491/chat-application-with-signalr-and-aspnet-mvc-4 Try to understand technology, how to apply it? |  |  | 3 | Todo
6 | Chat with video stream | Research and work around with WebRTC | Follow this instruction: http://www.skylinetechnologies.com/Blog/Article/48/Peer-to-Peer-Media-Streaming-with-WebRTC-and-SignalR.aspx Try to understand technology, how to apply it? |  |  | 3 | Todo
7 | Create medical profile | Define the structure of a medical profile | Get some common information from some hospitals and analyse them |  |  | 4 | Todo
8 | Basic design | Apply style for the initial project | Appy bootstrap as css framework | Homepage look nice |  | 4 | Todo
21

## Information
Member |  |  | Information
No. | Short Name | Fullname | 1. Kanban | https://trello.com/b/JditEulN/kanban-sprint-1
1 | Su | Trần Nguyên Tiến Sứ | 2. Velocity | 1 point/day
2 | Danh | Trần Cao Danh
3 | Dang | Trương Hải Đăng
4 | Tin | Bùi Nguyên Tín
Status
Todo
In-progress
Verify
Done
Accept